## Sheet1
SPRF | Suffix | Unique Identifier | Project Name | Program Name | Overall Status | Schedule Status | Estimate | Estimate Type | Release Date | Project | Comments
400032790 | R5 | 400032790R5 | Ovations Provider Pick Improvements |  | 4 - Complete | 3 - Completed | 22.82 | OOM | 2012-06-23 | Project | 6/22 CC 14 was cancelled and CC 15 was scheduled 4/16 Added 1.65 pm to 21.17 effort for CC 14 - cc still in estimating in prompt CC 12
400033231 | R5 | 400033231R5 | HIPAA 5010-UHC-835 RA |  | 4 - Complete | 3 - Completed | 0.48 | OOM | 2012-02-11 | Project | CC48
400037224 | R2 | 400037224R2 | Systems of Record - Data Interface 2011 H1 |  | 4 - Complete | 3 - Completed | 56.19 | OOM | 2012-03-10 | Project | 6/7 Changed estimate from 43.20 to 56.19 per Bridget CC 5
400037224 | R4 | 400037224R4 | Systems of Record - Data Interface 2011 H1 |  | 4 - Complete | 3 - Completed | 12.89 | OOM | 2012-05-12 | Project | 11/14 CC10 split between Q1 and Q2- reduced from 16.32 to 12.89 CC10 scheduled CC10 - CC still in estimating in prompt
400037224 | R6 | 400037224R6 | Systems of Record - Data Interface 2011 H1 |  | 4 - Complete | 3 - Completed | 3.44 | OOM | 2012-03-10 | Project | 11/14 CC10 split between Q1 and Q2 CC10 scheduled CC10 - CC still in estimating in prompt
400037224 | R7 | 400037224R7 | Systems of Record - Data Interface 2011 H1 |  | 4 - Complete | 3 - Completed | 2.92 | OOM | 2012-03-10 | Project | CC13
400037224 | R8 | 400037224R8 | Systems of Record - Data Interface 2011 H1 |  | 4 - Complete | 3 - Completed | 2.81 | OOM | 2012-05-12 | Project | CC12 - CC still in estimating in prompt
400040360 | A | 400040360A | Medical Necessity ICM |  | 4 - Complete | 3 - Completed | 85.51 | OOM | 2012-08-11 | Project | 8/20 Reduced estimate from 94.76 to 85.51 in DE cc 22. 6/22 CC 20, reduced estimate to 94.76 from 103 5/25 Per Mel reduced BGE to 103 and moved 6 pm's to Sept for UDW effort 5/4 Per Vicky - reduced from 122.77 to 116.52 - 2 came out fo cc8 12/12 Project now oom approved in proompt 10/10 Project funded but not yet oom approved in prompt - prompt has 147.57 but we reduced down to 98 pm's - no cc was opened. This estimate will be re-evaluated again once the analysis is completed.
400040360 | B | 400040360B | Medical Necessity ICM |  | 4 - Complete | 3 - Completed | 3.18 | OOM | 2012-09-22 | Project | CC15
400040360 | D | 400040360D | Medical Necessity ICM |  | 4 - Complete | 3 - Completed | 6 | OOM | 2012-09-22 | Project | 5/25 Per Mel reduced BGE in Aug to 103 and moved 6 pm's to Sept for UDW effort
400040360 | I | 400040360I | Medical Necessity ICM |  | 4 - Complete | 3 - Completed | 0 | OOM | 2012-11-10 | Project | 10/11/12 Added a line to show the deployment, but effort completed in September.
400041452 | D | 400041452D | Cont CDB Core Processing: Inc View Cutovers |  | 4 - Complete | 3 - Completed | 5.96 | OOM | 2012-05-12 | Project | CC2
400041737 | E | 400041737E | ICD10- Field Expansion- UHC EI |  | 4 - Complete | 3 - Completed | 7.41 | OOM | 2012-02-11 | Project | 11/14 Per Cathy - updating effort from 6.21 to 7.41 to include effort not burned on other deliverables for this sprf - 6.21 is what is in prompt 9/16 Project increased from 4.20 to 6.21 the additional 2 pm increase is under cc22 - CC 17 is now scheduled CC17 - still in estimating
400041737 | J | 400041737J | ICD10- Field Expansion- UHC EI |  | 4 - Complete | 3 - Completed | 46.4 | OOM | 2013-02-16 | Project | 7/20 CC now scheduled in prompt 6/8 CC 52 - cc still in est in Prompt
400042122 | A | 400042122A | 5010 EDI Reporting |  | 4 - Complete | 3 - Completed | 4.01 | OOM | 2012-06-23 | Project | CC2
400042400 | A | 400042400A | Automate online FL provider search & directory |  | 4 - Complete | 3 - Completed | 7.64 | OOM | 2012-03-10 | Project
400042400 | B | 400042400B | Automate online FL provider search & directory |  | 4 - Complete | 3 - Completed | 4.58 | OOM | 2012-03-10 | Project | 1/23 CC8 - Increased the amount from 3.88 to 4.58 10/31 Project oom approved CC6 -CC still in estimating in prompt
400042795 | E | 400042795E | PDR - EVC Fee Schedule Migration to NDB |  | 4 - Complete | 3 - Completed | 25.81 | OOM | 2012-02-11 | Project | 9/16 CC now scheduled in prompt CC 12 - CC still in estimating in prompt
400042795 | G | 400042795G | PDR - EVC Fee Schedule Migration to NDB |  | 4 - Complete | 3 - Completed | 1 | OOM | 2012-02-11 | Project | per Rev the 150 hours will be split among SA, Dev & QCA - most of work completed under CC13 this is for delivery and testing support - no prompt entry for this
400043123 | B | 400043123B | ER/HBP OON Fee schedule |  | 4 - Complete | 3 - Completed | 5.29 | OOM | 2012-05-12 | Project | 2/17/12 Estimate reduced per the design cc from 5.69 to 5.29 CC 11
400043359 | C | 400043359C | PM&R: Multiple Therapy Procedure Reduction |  | 4 - Complete | 3 - Completed | 4.89 | OOM | 2012-02-11 | Project | 2/12 CC12 Reduced estimate from 6.27 to 4.89 CC11
400043969 | A | 400043969A | SSN Randomization project - Eligibility sytems |  | 4 - Complete | 3 - Completed | 4.92 | OOM | 2012-05-12 | Project | 2/17/12 Increased estiamte in design cc from 3.08 to 4.92 pm's
400044267 | A | 400044267A | Medical Necessity - IPCM Contracting Scope |  | 4 - Complete | 3 - Completed | 77.44 | OOM | 2012-02-11 | Project | 12/30 Reduced from 78.97 to 77.44 in CC5 Reduced from 84.97 to 78.97 - 6pms moved out to May 2012
400044267 | B | 400044267B | Medical Necessity - IPCM Contracting Scope |  | 4 - Complete | 3 - Completed | 3.4 | OOM | 2012-02-11 | Project | CC2
400044267 | C | 400044267C | Medical Necessity - IPCM Contracting Scope |  | 4 - Complete | 3 - Completed | 2.58 | OOM | 2012-02-11 | Project | CC3
400044267 | D | 400044267D | Medical Necessity - IPCM Contracting Scope |  | 4 - Complete | 3 - Completed | 9.99 | OOM | 2012-02-11 | Project | CC4
400044267 | E | 400044267E | Medical Necessity - IPCM Contracting Scope |  | 4 - Complete | 3 - Completed | 6 | OOM | 2012-02-11 | Project | This is broken out from the OOM - no cc for this
400044781 | A | 400044781A | TBS Provider Data Quality - Bridge NDB Gaps |  | 4 - Complete | 3 - Completed | 57 | OOM | 2012-09-22 | Project | 6/22 Increased from 52 to 57 in CC10. Second piece of CC8 moved to 52217 so CC10 has a decrease for that piece as well as an increase for the September piece. 3/5 Est split between 2 releases - Q3 reduced from 65 pm's to 52 pm's CC8 is now scheduled CC8 - estimate not yet entered in prompt and cc still in estimating
400045320 | A | 400045320A | Transparency 1/1 Release |  | 4 - Complete | 3 - Completed | 84.67 | OOM | 2012-02-11 | Project | 1/23 Decreased estimate by 3.40 from 88.07 to 84.67 for cc( 10/10 Project OOM approved 9/30 Project in SC Changed estimate from 50 to 88.07 PM's
400045320 | B | 400045320B | Transparency 1/1 Release |  | 4 - Complete | 3 - Completed | 5.41 | OOM | 2012-03-10 | Project | 9/30 Project in SC - parf of the oom
400045320 | C | 400045320C | Transparency 1/1 Release |  | 4 - Complete | 3 - Completed | 3.4 | OOM | 2012-05-12 | Project | CC9 - zero is being added to prompt and the 3.4 is being taken from the oom
400045320 | D | 400045320D | Transparency 1/1 Release |  | 4 - Complete | 3 - Completed | 1.6 | OOM | 2012-03-10 | Project | 3/5 CC is now scheduled CC10 - zero is being added to prompt and the 1.64 is being taken from the oom
400045320 | UA | 400045320UA | Transparency 1/1 Release |  | 4 - Complete | 3 - Completed | 1.97 | OOM | 2012-02-11 | Project | 1/6 CC now scheduled 12/20 Estimates entered into prompt but cc still in estimating CC 2 - estimate not yet entered into prompt/waiting on NDB estimate to enter both - cc still in estimating
400045746 | B | 400045746B | HPHC Platform Based Joint Venture |  | 4 - Complete | 3 - Completed | 12.27 | OOM | 2012-08-11 | Project | 7/13 Added .31 in CC5 DE 4/30 Added 1.68 to increase from 10.28 to 11.96 in CC3 sol estimate CC1
400046103 | A | 400046103A | WA Implementation |  | 4 - Complete | 3 - Completed | 5.2 | OOM | 2012-05-12 | Project | 7/2 Reduced from 5.99 to 5.2 in CC 24 DE 4/19 Estimate reduced by 1 pm in Sol est 2/6/12 Project oom approved in prompt Project still in estimatng in prompt
400046131 | A | 400046131A | DME – Competitive Bidding Process |  | 4 - Complete | 3 - Completed | 57.08 | OOM | 2013-02-16 | Project | 12/13/12 Estimate increased from 53.88 to 57.08 -in cc11 DE. 8/10 Scope will increase by 20.51 from 33.37 to 53.88 - cc not opened yet in prompt 5/18 Estimate includes BGE and CC 2 effort
400046410 | C | 400046410C | ED - ISET-ELGS Integration |  | 4 - Complete | 3 - Completed | 2.93 | OOM | 2013-02-16 | Project | 11/9/12 estimate increased by .07 from 2.86 to 2.93 in CC 10 DE CC8
400047206 | A | 400047206A | HCR Preventive Care - Women's Health |  | 4 - Complete | 3 - Completed | 6.83 | OOM | 2012-08-11 | Project
400047477 | A | 400047477A | ICD10 E & I Compliance Release |  | 4 - Complete | 3 - Completed | 10.44 | OOM | 2012-06-23 | Project
400047477 | C | 400047477C | ICD10 E & I Compliance Release |  | 4 - Complete | 3 - Completed | 2.28 | OOM | 2013-02-16 | Project | 12/6/12 estimate increased in cc10 from 1.75 to 2.28 in DE for Q1 CC10 7/3 110 hours left on total project from June plus 1.02 pm's in CC 7 - code was completed in June 2012 but will be deployed into production.
400047648 | B | 400047648B | HI Quest Expansion |  | 4 - Complete | 3 - Completed | 3.11 | OOM | 2012-06-23 | Project | CC1
400047682 | A | 400047682A | EPDL KTLO 2012 |  | 4 - Complete | 3 - Completed | 59.77 | OOM | 2012-06-30 | Project
400047682 | B | 400047682B | EPDL KTLO 2012 |  | 4 - Complete | 3 - Completed | 6.36 | OOM | 2012-09-22 | Project
400047776 | A | 400047776A | NDB Cosmos Demo SoT - Facility Panels |  | 4 - Complete | 3 - Completed | 15 | OOM | 2012-06-23 | Project | 2/6/12 Decreased estimate from 63.61 to 15 pm's - There will be no code deploy for this piece Project still in estimating
400047776 | B | 400047776B | NDB Cosmos Demo SoT - Facility Panels |  | 4 - Complete | 3 - Completed | 71.9 | OOM | 2012-08-11 | Project | 7/30 Decreased from 81 to 71.9 in SE CC 9 4/30 Project oom approved 2/171/12 increased est for Q3 from 48.81 to 81 pm's Project still in estimating - working on a revised BGE where scope will increase - BGE est split between Q2 and Q3
400047776 | D | 400047776D | NDB Cosmos Demo SoT - Facility Panels |  | 4 - Complete | 3 - Completed | 10.39 | OOM | 2012-09-22 | Project | 4/30 Project oom approved CC2 - cc scheduled but project still not oom approved
400048088 | A | 400048088A | Health Care Cost Estimator R2 |  | 4 - Complete | 3 - Completed | 60.7 | OOM | 2012-08-11 | Project | 7/30 Per Cathy reduced by 6.67 pm's in cc 10 and this will be added to 50155 5/25 Increased from 58.07 to 67.37 in CC3 4/30 Reduced estimate per CC 2 which is still in estimating from 68.82 to 58.07. 2/17/12 BGE increased from 32.48 to 68.82 pm's 1/6 oom was 51.77, and the increase now puts the OOM at 62.48 Replacing 4-43230
400048089 | A | 400048089A | Common Pricing Solution- Anesthesia Enhancements |  | 4 - Complete | 3 - Completed | 22.49 | OOM | 2012-02-11 | Project | 1/23/12 CC1 reduced estimate from 25.81 to 22.49 pm's SPRF 400042795 CC12, PDR EVC Fee Schedules (PV – 42795D) is now opened as new SPRF 400048089,Common Pricing Solution- Anesthesia Enhancements.
400048140 | A | 400048140A | ICD-10 E& I Code Loading |  | 4 - Complete | 3 - Completed | 27.99 | OOM | 2012-11-10 | Project | 8/27 Increased estimate from 27.20 to 27.99 6/8 Reduced estimate from 37.07 to 27.2 in CC 3 and descoped the other 2 pieced of this project which moved to different sprf's. 5/25 Project being split so CC 3 to reduce other release effort - resulting in increas in this estimate from 33 to 37.07 5/18 BGE split into 3 releases - total is 124 pm's - BGE is only 116.99 - will need to true up in prompt
400048226 | A | 400048226A | HCR Preventative Care Additional Services |  | 4 - Complete | 3 - Completed | 26.75 | OOM | 2012-06-23 | Project
400048226 | B | 400048226B | HCR Preventative Care Additional Services |  | 4 - Complete | 3 - Completed | 4.37 | OOM | 2012-08-11 | Project
400048227 | A | 400048227A | NDB 2012 One Shot Requests |  | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-02-11 | Project | 2/17/12 Project now oom approved Project still in estimating in prompt
400048227 | B | 400048227B | NDB 2012 One Shot Requests |  | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-05-12 | Project | Project now oom approved Project still in estimating in prompt
400048227 | C | 400048227C | NDB 2012 One Shot Requests |  | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-08-11 | Project | Project now oom approved Project still in estimating in prompt
400048227 | D | 400048227D | NDB 2012 One Shot Requests |  | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-11-10 | Project | Project now oom approved Project still in estimating in prompt
400048416 | A | 400048416A | OnLine Referral Capability for Gatekeeper Products |  | 4 - Complete | 3 - Completed | 6.72 | OOM | 2012-12-08 | Project | 11/30/12 Reduced estimate in DE by .65 pm's from 7.37 to 6.72 9/27 Reduced estimate from 8.45 to 7.37 in CC 1 SE. 8/3 Includes CC 4 - increased 5.60 to 8.45
400048660 | A | 400048660A | CPS-COSMOS to NDB Fee Sched Pricing |  | 4 - Complete | 3 - Completed | 33.76 | OOM | 2012-08-11 | Project | 7/30 Reduced estimate from 35.09 to 33.76 in CC 6 DE 3/19 Revised the NDB estimate Project sitill in estimating
400048981 | A | 400048981A | WOQ1 NDB OI - Auto DBA Name Population |  | 4 - Complete | 3 - Completed | 4 | OOM | 2012-02-11 | Project | 1/6 WO now scheduled in prompt This is for OI00101 - 1.13 remaining effort entered into prompt
400048983 | A | 400048983A | WOQ1 NDB OI NDB FS Space Conservation Reporting |  | 4 - Complete | 3 - Completed | 0.74 | OOM | 2012-02-11 | Project | 1/6 WO now scheduled in prompt This is for OI00170 - .23 remaining effort entered into prompt
400048984 | A | 400048984A | WOQ1 NDB OI Add Specialty to 'P' Type Search |  | 4 - Complete | 3 - Completed | 4 | OOM | 2012-03-10 | Project | 1/6 WO now scheduled in prompt This is for OI00233 - 1.63 remaining effort entered into prompt
400048985 | A | 400048985A | WOQ1 NDB OI NDC MAC Pricing |  | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-03-10 | Project | This is for OI00250 - 1.33 remaining effort entered into prompt
400049163 | A | 400049163A | WOQ1 NDB OI Retrigger BSAR History |  | 4 - Complete | 3 - Completed | 1.9 | OOM | 2012-02-11 | Project | 1/6 WO now scheduled in prompt This is for OI00294 - 1.53 entered into prompt for remaining effort
400049235 | A | 400049235A | Q2 NDB OI 00260 Navigate Adr Seq for EPDL |  | 4 - Complete | 3 - Completed | 9.16 | OOM | 2012-06-30 | Project
400049237 | A | 400049237A | Q2 NDB OI 00290 Involuntary Sanction |  | 4 - Complete | 3 - Completed | 9.03 | OOM | 2012-06-23 | Project
400049238 | A | 400049238A | Q2 NDB OI 00296 C&S Group BSAR Term |  | 4 - Complete | 3 - Completed | 7.93 | OOM | 2012-06-23 | Project | 6/8 increased est from 6.90 to 7.93 in CC 2 sol est
400049798 | A | 400049798A | Kansas Medicaid - KanCare Implementation |  | 4 - Complete | 3 - Completed | 5.11 | OOM | 2012-10-24 | Project | 11/9/2012 Decreased in DE CC 28 from 6.07 to 5.11 9/5/12 Estimate decreased from 16.85 to 6.07 8/24/12 Changed release date from 11/10/12 to 11/1/12 On Shore Support only
400049913 | A | 400049913A | NDB EPDE/EPDL 2012 |  | 4 - Complete | 3 - Completed | 10.89 | OOM | 2013-03-02 | Project
400049913 | UA | 400049913UA | NDB EPDE/EPDL 2012 |  | 4 - Complete | 3 - Completed | 0.95 | OOM | 2013-02-16 | Project
400050155 | A | 400050155A | Health Care Cost Estimator Release 2.2 |  | 4 - Complete | 3 - Completed | 123 | OOM | 2012-11-10 | Project | 10/17 Project now BGE Approved in prompt. 10/4 Estimate increased from 120 to 123. 9/10/12 Reduced estimate from 129 to 120 per CC1. 8/24 Split BGE estimate between 2 reelases so this one reduced from 184.51 to 129 8/10 BGE increased to 184.51 from 143.36 5/25 Updated est from 112.51 to 143.36 per revised bge 5/11 Updated est to 112.51 due to revised bge Project still in estimating
400050155 | C | 400050155C | Health Care Cost Estimator Release 2.2 |  | 4 - Complete | 3 - Completed | TBD | OOM | 2012-12-08 | Project | 10/17 Project now BGE Approved in prompt. 10/11/2012 Cathy is working on the split and will get back to us.
400050155 | E | 400050155E | Health Care Cost Estimator Release 2.2 |  | 4 - Complete | 3 - Completed | 4.18 | OOM | 2013-03-02 | Project | 4/12 CC 16 is now scheduled in Prompt 1/2/13 CC16 - CC still in estimating in Prompt
400050155 | UA | 400050155UA | Health Care Cost Estimator Release 2.2 |  | 4 - Complete | 3 - Completed | 1.43 | OOM | 2012-11-10 | Project
400050564 | A | 400050564A | RSASL-Navigate Referral Summary & Detail Report |  | 4 - Complete | 3 - Completed | 2.88 | OOM | 2012-08-11 | Project | 8/20 Decreased from 3.45 to 2.88. 7/2 Increased estimate from 2.70 to 3.45 per CC 3 SE.
400050630 | A | 400050630A | NDB SoT - C&S Strategic NDB SoT Enhancements A/D |  | 4 - Complete | 3 - Completed | 146.2 | OOM | 2012-12-08 | Project | 12/6/12 Per pm moved 10 pm's to Jan2013 release 9/17 Revised DE should be 146.2 8/24 Decreased est in DE from 161.71 to 135.11 6/8 Decreased est in CC 1 sol est from 179.89 to 161.71 4/6 changed effort from 185.89 to 179.89 - 6 pms moved to Sept release
400050630 | E | 400050630E | NDB SoT - C&S Strategic NDB SoT Enhancements A/D |  | 4 - Complete | 3 - Completed | 10 | OOM | 2013-01-26 | Project | 12/6/12 Per pm moved 10 pm's to Jan2013 release
400050954 | A | 400050954A | NDB CD- Market Type ID Tactical Solution |  | 4 - Complete | 3 - Completed | 30.01 | OOM | 2012-08-11 | Project | 7/30 Estimate will be reduced in cc 5 by 4.8 pm's 5/11 Decreased est due to split for Sept 5/4 Added additonal effort - from 34.81 to 42.14 per revised bge by AM 3/26 Project in est - sched per Vicky- BGE split between Aug and Sept
400050954 | B | 400050954B | NDB CD- Market Type ID Tactical Solution |  | 4 - Complete | 3 - Completed | 7.33 | OOM | 2012-09-22 | Project | 4/19 Project in est - sched per Vicky- BGE split between Aug and Sept
400050954 | D | 400050954D | NDB CD- Market Type ID Tactical Solution |  | 4 - Complete | 3 - Completed | 0 | OOM | 2012-11-10 | Project | 10/11/12 Added a line to show the deployment, but effort completed in September.
400051104 | A | 400051104A | WOQ2 01 Navigate Provider Contract One Shots |  | 4 - Complete | 3 - Completed | 6.65 | OOM | 2012-08-11 | Project | 7/13 Per Sean moved to Aug
400051300 | A | 400051300A | UNO Replacement A/D |  | 4 - Complete | 3 - Completed | 4.96 | OOM | 2013-02-16 | Project | 11/301/12 Estimate reduced in DE by .89 hours from 5.85 to 4.96
400052233 | UA | 400052233UA | TX ERS - WorkStream1: Data Segmentation and Securi |  | 4 - Complete | 3 - Completed | 1.71 | OOM | 2012-08-11 | Project | 10/17 Project now BGE Approved in prompt. 7/2 Project not scheduled or oom approved in prompt
400052244 | A | 400052244A | TX ERS - WorkStream2: Core Processing |  | 4 - Complete | 3 - Completed | 4.84 | OOM | 2012-08-11 | Project | 8/3 Project now oom approved in Prompt 7/2 Project now in IT Leadership Review Project still in estimating in prompt
400052259 | A | 400052259A | TX ERS - WorkStream3: Portals, Constituent Servic |  | 4 - Complete | 3 - Completed | 4.56 | OOM | 2012-08-11 | Project | 5/25/12 Project still in estimating in prompt
400052619 | A | 400052619A | Ohio Migration |  | 4 - Complete | 3 - Completed | 19.42 | OOM | 2013-01-23 | Project | 2/1/13 Increased estimate from 18.79 to 19.42 - DE CC 13 - increase of .63 8/3 Estimate includes BGE and CC 1
400053105 | A | 400053105A | UMR myHCE integration |  | 4 - Complete | 3 - Completed | 4.18 | OOM | 2012-09-22 | Project | BGE will be split into 2 releases this piece going in for Q3B - project type may change to tech only or work order
400053723 | A | 400053723A | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 110.9 | OOM | 2012-11-10 | Project | 10/11 Per Janine estimate adjusted from 102.94 to 110.9. 9/17 Project now BGE approved in prompt. 9/10/12 Tricare being broken down into more releases, therefore the estimate for November has changed. 8/3 BGE split between Q4 12 and Q1 13 - project not bge approved yet in prompt
400053723 | B | 400053723B | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 58.56 | OOM | 2013-02-16 | Project | 1/4/13 Added 8.9 pm's from 49.66 to 58.56 per split of DE CC 12 from Janine 10/11 Per Janine estimate adjusted from 46.95 to 49.66-Includes the Tracer ID Search capabilities. 10/4 Increased estimate from 41.24 to 46.95. 9/27 Breakout changes per Vicky for February decrease. 9/17 Project now BGE approved in prompt. 9/10/12 Tricare being broken down into more releases, therefore the estimate for February has changed. 8/3 BGE split between Q4 12 and Q1 13 - project not bge approved yet in prompt
400053723 | C | 400053723C | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 15.33 | OOM | 2012-12-08 | Project | 10/11 Per Janine estimate adjusted from 15.44 to 15.33. 9/27 Breakout change per Vicky for December increase. 9/10/12 Estimate part of bge
400053723 | E | 400053723E | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 91.66 | OOM | 2013-03-02 | Project | 5/23 CC 21 Scheduled in Prompt 5/10 Added 7.74 to increase from 83.92 to 91.66 in CC 21 2/16 Added 7 pm's to increase from 76.92 to 83.92 in CC 17 1/25 Added .98 pm in CC 15 - increased effort from 75.94 to 76.92 1/4/13 Added 4.91 pm's from 71.03 to 75.94per split of DE CC 12 from Janine 9/10/12 Search and Directory piece. This includes the SE
400053723 | G | 400053723G | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 0 | OOM | 2013-03-02 | Project | 2/1 Added line for EPDL for Tricare - will get split later
400053723 | UA | 400053723UA | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 2.85 | OOM | 2012-11-10 | Project | 9/17 Project now BGE approved in prompt. 8/3 project not bge approved yet in prompt
400053723 | UB | 400053723UB | TRICARE West Implementation FD: Provider/Network |  | 4 - Complete | 3 - Completed | 0 | OOM | 2013-02-16 | Project | Added line for USEC dep in Feb - effort included in Feb Tricare release - for tracking purpose only
400054333 | UA | 400054333UA | NDB Role Based Security Access |  | 4 - Complete | 3 - Completed | 17.08 | OOM | 2012-11-10 | Project | 10/11 Project now BGE Approved in prompt. 8/24 Project still in estimating in prompt
400054445 | A | 400054445A | Medical Necessity IPCM Phase 2 |  | 4 - Complete | 3 - Completed | 3.33 | OOM | 2013-02-16 | Project | 1/14/13 BGE approved in Prompt 10/17/12 Project still in estimating in prompt.
400054944 | A | 400054944A | Kansas BH Claims Processing on CSP & Careone |  | 4 - Complete | 3 - Completed | 0.46 | OOM | 2012-12-12 | Project | 12/28/12 In CC 5 DE backed out 2.11 pm's to decrease from 2.57 to .46 10/4 Project now OOM Approved in prompt. 9/21/12 Replacing SPRF 4-49798 CC1. Project still in estimating in prompt.
400054944 | C | 400054944C | Kansas BH Claims Processing on CSP & Careone |  | 4 - Complete | 3 - Completed | 0.95 | OOM | 2012-12-12 | Project | CC 3
411111111 | A | 411111111A | Provider Touchpoint Reduction Pilot |  | 4 - Complete | 3 - Completed | 7.16 | OOM | 2012-03-30 | Project | 1/23 Added additional scope - increased from 4 to 7.16 pm's
OI00101 | R1 | OI00101R1 | Auto DBA Name Population | Other | 4 - Complete | 3 - Completed | 4 | OOM | 2012-02-11 | Project
OI00233 | R1 | OI00233R1 | Add Specialty to ‘P’ Type Search | Other | 4 - Complete | 3 - Completed | 4 | OOM | 2012-03-10 | Project
OI00245 | R1 | OI00245R1 | Change in Display NBB Selection Screen |  | 4 - Complete | 3 - Completed | 3.6 | OOM | 2012-05-12 | Project
OI00250 | R1 | OI00250R1 | NDC MAC Pricing | Other | 4 - Complete | 3 - Completed | 2.5 | OOM | 2012-03-10 | Project
OI00294 | R1 | OI00294R1 | Retrigger BSAR History | Other | 4 - Complete | 3 - Completed | 1.9 | OOM | 2012-02-11 | Project